**Project Status Report III**

|  |
| --- |
| **Date of Report Issue/Prepared**: March 6 2019 |

**Report Prepared By**: Fortune Creig Phiri,Sherwayne Walrond , Paul Ajibola

**Employer/Organization**: Self Care

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | **SelfCare** | |
| **T\_12** | |
| **Start Date: Feb 02, 2019** | **End Date: Mar 08, 2019** |
| **Red (Bad)** | |

Summary

|  |
| --- |
| **Project Status Summary** |
| Project is currently behind schedule. Efforts and measures are currently in place to mitigate the risks the project is currently facing, which entails a team restructure placing members in more efficient roles |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| General User - User Interface. The views/ screens for the | General user booking functionality- the user should be able to make to schedule an appoint with the service provider |
| General user should be able to search for professionals | List of professional user’s bookings- system should be able to give the professional users bookings |
| Basic professional backend search criteria completed on the backend | Facebook and google login |
|  | Image uploads to amazon web services |

Upcoming Objectives for Mar 9, 2019 to March 31, 2019

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Planned Activities/Tasks for Next Period** | | | | |
| **Activity/Task** | **Assigned To** | | **Duration** | **Date** |
| User Interface for the professional user Screens(User Account , Bookings ,HomeScreen, Instant messaging ) | Creig | | 1 week | March 10 2019 |
| Google maps integration (figuring out the close address to a user) | Sherwayne | | 10 days | March 10 2019 |
| Complete and connect Registration and Login backend to front-end | Paul Ajibola | | March 10 - March 16, 2019 | March 10, 2019 |
|  |  |  |  |  |
|  |  |  |  |  |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Members are behind on scheduled tasks. | Restructuring of of team roles. More scheduled peer coding sessions | March 10 2019 |
| Poor communication between team members | Setting 3-day status updates | March 30 2019 |
| Lack of contribution/Participation | Do what we can with who shows up | March 10 2019 |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Risk that project will not be completed within by the deadline | HIGH | HIGH | Restructure of project roles to allow for better efficiency |
| Risk that project will not be deployed to Play-Store and App-store by the relevant dates | HIGH | HIGH | Place deadlines set from now until March 31st on high priority |

**NOTE: Attach additional sheets if insufficient space available**

|  |  |  |  |
| --- | --- | --- | --- |
| **Project Tasks** |  | | |
|  | **Member** | | |
|  | **Sherwayne** | **Paul** | **Fortune Creig** |
| Planning and Scheduling | **R** | **R** | **R** |
| UI design and Functionality | **C** | **C** | **A** |
| System Testing | **R** | **R** | **R** |
| Backend functionality | **A** | **A** | **C** |

**Legend**

**C :** Consulted **; R :** Responsible **; A :** Accountable **; I :**Informed

**Project tasks and work done**

The project tasks were created and divided in a manner that each was independent of the other. Where team members were assigned

|  |  |
| --- | --- |
| **Fortune Creig Phiri Tasks** | |
| **Tasks** | **Completion** |
| General user UI (Screen) | 90% |
| Professional search and filters | 90% |
| Professional User Screens | 40% |
| Google integration, getting users current location | 0% |
| Application navigation | 100% |
| Administrator Views (Screens) | 0% |

|  |  |
| --- | --- |
| **Sherwayne Walrond Tasks** | |
| **Tasks** | **Completion** |
| Node.js server setup | 100% |
| Database integration and creation | 100% |
| API routing and Model creation | 80% |
| Google Maps API Integration | 0% |
| Messaging | 0% |
| Booking System | 0% |

|  |  |
| --- | --- |
| **Paul Ajibola Tasks** | |
| **Tasks** | **Completion** |
|  |  |
|  |  |
|  |  |
|  |  |

|  |  |  |
| --- | --- | --- |
|  | |  |
| **Team \_12\_** | **Capstone Project II**  **Minutes of Meeting # \_4\_**  **Date: March 06 2019**  **Time: 10:00am**  **Location: Casa Loma Campus** |  |
|  | |  |
|  | |  |
| **Attendees:** | Team member 1: Sherwayne Walrond Team member 3: Ife Ajibola  Team member 2: Fortune Creig Phiri |  |
|  | |  |
| **Agenda** | |  |
| **Item** | **Description** | **Responsibility** |
| **Review of previous meeting** | The previous meeting was on the creation of a user friendly UI. The concerns for the backend were for those members tasked with working on the backend to observe good coding standards. The main agenda for the meeting was on ensuring that every member of the team observed set deadlines and goals. | All |
| Item # 1…Google maps | Integrating google maps to application backend. | Sherwayne |
| Item # 2… Socket.io integration | Integrate messaging to backend . | Sherwayne |
| Item # 3… Allowing user to make a booking | Integrate booking system to backend. | Sherwayne |
| Item # 4.. | Integrating google maps to application to get user location | Fortune Creig |
| Item #5…. | Creating instant messaging views | Fortune Creig |
| Item # 6.... | Adhering to set deadlines, targets (both short and long). In the meeting it was stressed how the team was behind schedule, and the project was in the danger zone. | All |
| **Next meeting date** | Date: March 15, 2019  Time: 10:00am  Location: C406  **Signature:**  Team member 1: Sherwayne Walrond  Team member 2: Fortune Creig Phiri  Team member 3: Ife Ajibola | All |